## Iteration 1
User Story | Job Assignment | Days Left/Effort Left
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | 54 | 51 | 51 | 54 | 51 | 38 | 31 | 26
Create a Web Server Skeleton | CH | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 0; Days Left/Effort Left 2: 0; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 0; Days Left/Effort Left 5: 0; Days Left/Effort Left 6: 0; Days Left/Effort Left 7: 0
Create a Main Page Skeleton | CH | Days Left/Effort Left 0: 10; Days Left/Effort Left 1: 10; Days Left/Effort Left 2: 10; Days Left/Effort Left 3: 10; Days Left/Effort Left 4: 10; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0
Create an App Submission Form Skeleton | MJ | Days Left/Effort Left 0: 7; Days Left/Effort Left 1: 7; Days Left/Effort Left 2: 7; Days Left/Effort Left 3: 7; Days Left/Effort Left 4: 7; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0
Create a New User Account | AS | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1
Create a Moderator Account | AS | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1
Create and Admin Type Account | AS | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1
Create the Logo | RV | bar: Days Left/Effort Left 0 to Days Left/Effort Left 7
Login to Your Account |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2
Create a Rating System for Apps |  | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3
Comment on an App |  | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3
Create the App Page |  | Days Left/Effort Left 0: 7; Days Left/Effort Left 1: 7; Days Left/Effort Left 2: 7; Days Left/Effort Left 3: 7; Days Left/Effort Left 4: 7; Days Left/Effort Left 5: 7; Days Left/Effort Left 6: 7; Days Left/Effort Left 7: 7
Set up Admin approval for all app submissions |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2
Set up moderator ability to delete comments | bar: Days Left/Effort Left 0 to Days Left/Effort Left 7
Video and picture submission for app |  | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3
Compare the same app across platforms |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2
Search fuctions of the database |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2

## Iteration 2
Iteration Deadline: | April 23rd
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Iteration 3
Iteration Deadline: | May 7th
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0