## Iteration 1
Iteration Deadline: | April 9th
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 26 | 26 | 29 | 26 | 13 | 5 | 0
Create a Web Server Skeleton |  | CH | Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0
Create a Main Page Skeleton |  | CH | Days Left/Effort Left 7: 10; Days Left/Effort Left 8: 10; Days Left/Effort Left 9: 10; Days Left/Effort Left 10: 10; Days Left/Effort Left 11: 10; Days Left/Effort Left 12: 3; Days Left/Effort Left 13: 1
Create an App Submission Form Skeleton |  | MJ | Days Left/Effort Left 7: 7; Days Left/Effort Left 8: 7; Days Left/Effort Left 9: 7; Days Left/Effort Left 10: 7; Days Left/Effort Left 11: 7; Days Left/Effort Left 12: 3; Days Left/Effort Left 13: 1
Create a New User Account |  | AS | Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 3; Days Left/Effort Left 9: 3; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 3; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 1
Create a Moderator Account |  | AS | Days Left/Effort Left 7: 2; Days Left/Effort Left 8: 2; Days Left/Effort Left 9: 2; Days Left/Effort Left 10: 2; Days Left/Effort Left 11: 2; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 1
Create and Admin Type Account |  | AS | Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 3; Days Left/Effort Left 9: 3; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 3; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 1
Create the Logo |  | RV | Days Left/Effort Left 7: 1; Days Left/Effort Left 8: 1; Days Left/Effort Left 9: 1; Days Left/Effort Left 10: 1; Days Left/Effort Left 11: 1; Days Left/Effort Left 12: 1; Days Left/Effort Left 13: 0

## Iteration 2
Iteration Deadline: | April 23rd
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Iteration 3
Iteration Deadline: | May 7th
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0