## Iteration 1
[8 empty] | Velocity: |  |  |  | 0.7
User Story | Job Assignment | Days Left/Effort Left
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
|  | 100 | 95.7143 | 95.7143 | 100 | 95.7143 | 77.1429 | 67.1429 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 58.5714 | 52.8571 | 52.8571 | 41.4286 | 41.4286
|  | 70 | 67 | 67 | 70 | 67 | 54 | 47 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 37 | 37 | 29 | 29
Create a Web Server Skeleton | CH | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 0; Days Left/Effort Left 2: 0; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 0; Days Left/Effort Left 5: 0; Days Left/Effort Left 6: 0; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create a Main Page Skeleton | CH | Days Left/Effort Left 0: 10; Days Left/Effort Left 1: 10; Days Left/Effort Left 2: 10; Days Left/Effort Left 3: 10; Days Left/Effort Left 4: 10; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create an App Submission Form Skeleton | MJ | Days Left/Effort Left 0: 7; Days Left/Effort Left 1: 7; Days Left/Effort Left 2: 7; Days Left/Effort Left 3: 7; Days Left/Effort Left 4: 7; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create a New User Account | AS | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create a Moderator Account | AS | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create and Admin Type Account | AS | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create the Logo | RV | Days Left/Effort Left 0: 1; Days Left/Effort Left 1: 1; Days Left/Effort Left 2: 1; Days Left/Effort Left 3: 1; Days Left/Effort Left 4: 1; Days Left/Effort Left 5: 1; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 0; Days Left/Effort Left 8: 0; Days Left/Effort Left 9: 0; Days Left/Effort Left 10: 0; Days Left/Effort Left 11: 0; Days Left/Effort Left 12: 0; Days Left/Effort Left 13: 0; Days Left/Effort Left 14: 0; Days Left/Effort Left 15: 0; Days Left/Effort Left 16: 0; Days Left/Effort Left 17: 0; Days Left/Effort Left 18: 0; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Login to Your Account | AS | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2; Days Left/Effort Left 8: 2; Days Left/Effort Left 9: 2; Days Left/Effort Left 10: 2; Days Left/Effort Left 11: 2; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 2; Days Left/Effort Left 14: 2; Days Left/Effort Left 15: 2; Days Left/Effort Left 16: 2; Days Left/Effort Left 17: 1; Days Left/Effort Left 18: 1; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 1
Create a Rating System for Apps | MJ | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 3; Days Left/Effort Left 9: 3; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 3; Days Left/Effort Left 12: 3; Days Left/Effort Left 13: 3; Days Left/Effort Left 14: 3; Days Left/Effort Left 15: 3; Days Left/Effort Left 16: 3; Days Left/Effort Left 17: 3; Days Left/Effort Left 18: 3; Days Left/Effort Left 19: 3; Days Left/Effort Left 20: 3
Comment on an App | MJ | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 3; Days Left/Effort Left 9: 3; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 3; Days Left/Effort Left 12: 3; Days Left/Effort Left 13: 3; Days Left/Effort Left 14: 3; Days Left/Effort Left 15: 3; Days Left/Effort Left 16: 3; Days Left/Effort Left 17: 3; Days Left/Effort Left 18: 3; Days Left/Effort Left 19: 3; Days Left/Effort Left 20: 3
Create the Skeleton of the App Page | CH, RV | Days Left/Effort Left 0: 7; Days Left/Effort Left 1: 7; Days Left/Effort Left 2: 7; Days Left/Effort Left 3: 7; Days Left/Effort Left 4: 7; Days Left/Effort Left 5: 7; Days Left/Effort Left 6: 7; Days Left/Effort Left 7: 7; Days Left/Effort Left 8: 7; Days Left/Effort Left 9: 7; Days Left/Effort Left 10: 7; Days Left/Effort Left 11: 7; Days Left/Effort Left 12: 7; Days Left/Effort Left 13: 7; Days Left/Effort Left 14: 7; Days Left/Effort Left 15: 7; Days Left/Effort Left 16: 7; Days Left/Effort Left 17: 6; Days Left/Effort Left 18: 6; Days Left/Effort Left 19: 5; Days Left/Effort Left 20: 5
Set up Admin approval for all app submissions | AS | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2; Days Left/Effort Left 8: 2; Days Left/Effort Left 9: 2; Days Left/Effort Left 10: 2; Days Left/Effort Left 11: 2; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 2; Days Left/Effort Left 14: 2; Days Left/Effort Left 15: 2; Days Left/Effort Left 16: 2; Days Left/Effort Left 17: 2; Days Left/Effort Left 18: 2; Days Left/Effort Left 19: 2; Days Left/Effort Left 20: 2
Submit an App to the Database | MJ | Days Left/Effort Left 0: 1; Days Left/Effort Left 1: 1; Days Left/Effort Left 2: 1; Days Left/Effort Left 3: 1; Days Left/Effort Left 4: 1; Days Left/Effort Left 5: 1; Days Left/Effort Left 6: 1; Days Left/Effort Left 7: 1; Days Left/Effort Left 8: 1; Days Left/Effort Left 9: 1; Days Left/Effort Left 10: 1; Days Left/Effort Left 11: 1; Days Left/Effort Left 12: 1; Days Left/Effort Left 13: 1; Days Left/Effort Left 14: 1; Days Left/Effort Left 15: 1; Days Left/Effort Left 16: 1; Days Left/Effort Left 17: 1; Days Left/Effort Left 18: 1; Days Left/Effort Left 19: 0; Days Left/Effort Left 20: 0
Create App Database | MJ | Days Left/Effort Left 0: 5; Days Left/Effort Left 1: 5; Days Left/Effort Left 2: 5; Days Left/Effort Left 3: 5; Days Left/Effort Left 4: 5; Days Left/Effort Left 5: 5; Days Left/Effort Left 6: 5; Days Left/Effort Left 7: 5; Days Left/Effort Left 8: 5; Days Left/Effort Left 9: 5; Days Left/Effort Left 10: 5; Days Left/Effort Left 11: 5; Days Left/Effort Left 12: 5; Days Left/Effort Left 13: 5; Days Left/Effort Left 14: 5; Days Left/Effort Left 15: 5; Days Left/Effort Left 16: 5; Days Left/Effort Left 17: 4; Days Left/Effort Left 18: 4; Days Left/Effort Left 19: 1; Days Left/Effort Left 20: 0
Set up moderator ability to delete comments | AS | bar: Days Left/Effort Left 0 to Days Left/Effort Left 20
Create the HTML Visual of all Pages | CH, RV | Days Left/Effort Left 0: 10; Days Left/Effort Left 1: 10; Days Left/Effort Left 2: 10; Days Left/Effort Left 3: 10; Days Left/Effort Left 4: 10; Days Left/Effort Left 5: 10; Days Left/Effort Left 6: 10; Days Left/Effort Left 7: 10; Days Left/Effort Left 8: 10; Days Left/Effort Left 9: 10; Days Left/Effort Left 10: 10; Days Left/Effort Left 11: 10; Days Left/Effort Left 12: 10; Days Left/Effort Left 13: 10; Days Left/Effort Left 14: 10; Days Left/Effort Left 15: 10; Days Left/Effort Left 16: 10; Days Left/Effort Left 17: 9; Days Left/Effort Left 18: 9; Days Left/Effort Left 19: 7; Days Left/Effort Left 20: 7
Video and picture submission for app |  | Days Left/Effort Left 0: 3; Days Left/Effort Left 1: 3; Days Left/Effort Left 2: 3; Days Left/Effort Left 3: 3; Days Left/Effort Left 4: 3; Days Left/Effort Left 5: 3; Days Left/Effort Left 6: 3; Days Left/Effort Left 7: 3; Days Left/Effort Left 8: 3; Days Left/Effort Left 9: 3; Days Left/Effort Left 10: 3; Days Left/Effort Left 11: 3; Days Left/Effort Left 12: 3; Days Left/Effort Left 13: 3; Days Left/Effort Left 14: 3; Days Left/Effort Left 15: 3; Days Left/Effort Left 16: 3; Days Left/Effort Left 17: 3; Days Left/Effort Left 18: 3; Days Left/Effort Left 19: 3; Days Left/Effort Left 20: 3
Compare the same app across platforms |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2; Days Left/Effort Left 8: 2; Days Left/Effort Left 9: 2; Days Left/Effort Left 10: 2; Days Left/Effort Left 11: 2; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 2; Days Left/Effort Left 14: 2; Days Left/Effort Left 15: 2; Days Left/Effort Left 16: 2; Days Left/Effort Left 17: 2; Days Left/Effort Left 18: 2; Days Left/Effort Left 19: 2; Days Left/Effort Left 20: 2
Search fuctions of the database |  | Days Left/Effort Left 0: 2; Days Left/Effort Left 1: 2; Days Left/Effort Left 2: 2; Days Left/Effort Left 3: 2; Days Left/Effort Left 4: 2; Days Left/Effort Left 5: 2; Days Left/Effort Left 6: 2; Days Left/Effort Left 7: 2; Days Left/Effort Left 8: 2; Days Left/Effort Left 9: 2; Days Left/Effort Left 10: 2; Days Left/Effort Left 11: 2; Days Left/Effort Left 12: 2; Days Left/Effort Left 13: 2; Days Left/Effort Left 14: 2; Days Left/Effort Left 15: 2; Days Left/Effort Left 16: 2; Days Left/Effort Left 17: 2; Days Left/Effort Left 18: 2; Days Left/Effort Left 19: 2; Days Left/Effort Left 20: 2
Note on AE20: Morgan Jacobson: 04/16
Note on AL20: Morgan Jacobson: 04/23
Note on AS20: Morgan Jacobson: 04/31
Note on AZ20: Morgan Jacobson: 04/07

## Iteration 2
Iteration Deadline: | April 23rd
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Iteration 3
Iteration Deadline: | May 7th
User Story |  | Job Assignment | Days Left/Effort Left
|  |  | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0